## Sprint Calendar
| Ash | Box | Cockle | Date | Elder | Flag | Grace | Hawthorn | Ivy | Kecksies | Ling | Mace | Narcissus | Oxlip
Start Date | 2021-07-05 | 2021-07-21 | 2021-08-04 | 2021-08-18 | 2021-09-01 | 2021-09-15 | 2021-09-29 | 2021-10-13 | 2021-10-27 | 2021-11-10 | 2021-11-24 | 2021-12-08 | 2021-12-22 | 2022-01-05
End Date | 2021-07-20 | 2021-08-03 | 2021-08-17 | 2021-08-31 | 2021-09-14 | 2021-09-28 | 2021-10-12 | 2021-10-26 | 2021-11-09 | 2021-11-23 | 2021-12-07 | 2021-12-21 | 2022-01-04 | 2022-01-18
|  | Wireframe and Spec WBEZ App 9.0 | WBEZ App | [6 empty] | Wireframe and Spec WBEZ App 9.1 | Develop WBEZ Mobile App v9.1 -> w/ Push Notifications |  |  | Hack Days???
Design | 2021-07-21: Wireframe collapsed audio player; 2021-08-04: Wireframe expanded player; 2021-08-18: Wireframe show/podcast pages; 2021-10-13: UX flow for search; 2021-11-24: UX flow for notifications
|  | Wireframe homepage |  | Mid-Fi prototype for board meeting | Wireframe & finalize homepage |  |  |  | Wireframe search |  |  | Wireframe notifications
Development | 2021-08-18: Develop WBEZ APP 9.0; 2021-10-13: Submit WBEZ App target: 10/26; 2021-10-27: Release WBEZ App 11/1; 2021-11-24: Develop App v9.1 search; 2021-12-22: Develop App v9.1 notifications
|  |  | ` |  | CMS Search Improvements & Dashboard | [5 empty] | Support Push Notification Tooling
QA | 2021-08-18: QA App audio player

## Future Epics Unsched.
(Priority) | Epic | Description | Context | Slate Goal | Key
| Accessibility Epic: Text contrast, font size, light/dark options** | CMS Dashboard Improvement Opps |  | 9/1-9/14 | Websites
↑ | Accessibility Epic: Text contrast, font size, light/dark options**? | Fix Accessibility on Stories |  | 9/1-9/14 | Mobile App
| CMS Story Edit IMG search | shorthand search for images w/n Story Edit isn't useful for producers, filter down to WBEZ/NPR img only | https://wbez.slack.com/archives/C01UDJM0M2Q/p1627951901001300 | 9/1-9/14 | Revenue
| Related Stories Search improvements | Better SEO on Google - Your Local News |  | 9/1-9/14
| "Interactive" templates for WBEZ.org |  |  | 9/15-9/28 | CMS
| FE Map Embed Template | MAP: Latest Update Of The Confirmed COVID-19 Case Count In Illinois |  | 9/15-9/28 | Dev Ops
| Data Visuals Style Guide (Ferris Cookbook?) | how you build a chart, step-by-step, using our CMS (collab w. Charmaine Ruse)
↑
| Overhaul WBEZ.org search | switch between listen/read - byline/topic filters - general improvements
↑ | Render Newsletters as Web Pages | (Show) The Rundown: WBEZ’s Daily Newsletter
| WBEZ Feature Series widget/player (Listen here: P1/2/3) | CMS Audio Upload feature - series dropdown, end reliance on inline embeds
| Podcast Player story page template w/ transcript | CMS Feature to offer WBEZ Story/2way web build outs, in lieu of a story (or in addition to...) Otter integration req?
| Invalidate Unpublished Stories w/out valid Preview URL | embargo fiasco (minor feature)
↑ | Archival Search and Retrieval Tool for Journalists' Use
| IG Stories Template e.g. "At Last, Hugs" | Reflections From The Class Of 2021
CMS Project Phase 2 - replace the FE Angular application
CA Infrastructre Upgrades.
| Desktop Livestreaming improvements | Steep declines from last year, make live listening option more prominent?
"New from Our Journalists" (like LAist.com)
Homepage Design Refresh
Case Creation with Rest API
Interns Page
Newsletter Hub
SMS Capture Affordance
Add to Homescreen icon - WBEZ.org
Expanded Affordance Interactions
More CA Batch Imports - By Summer?
Push Notifications on the Web
SMS Editorial Notifications
Mobile App Push notifications
Push Notifications from Vocalo App - can't miss programming
Sustainers Migration from NGOC to Springboard?
Vocalo.org redesign
Iterations on Vocalo App
Automated Airchecks for Archives
| Chicago News Update as a product (smart speaker skill) | Alexa & Google, specify "podcast" successful smart speaker use on all platforms

## Future Epics Unscheduled (hidden)
Epic | Description
NPSP Migration
Sustainers Migration from NGOC to Springboard?
Overhaul WBEZ.org search
Overhaul WBEZ App - direction TBD
"Interactive" templates for WBEZ.org
Vocalo.org redesign
Iterations on Vocalo App
Automated Airchecks for Archives
CMS Project Phase 2 - replace the FE Angular application
Newsletter Hub
SMS Capture Affordance
Add to Homescreen icon - WBEZ.org
Expanded Affordance Interactions
Chicago News Update as a product (smart speaker skill)
Push Notifications on the Web
SMS Editorial Notifications
Mobile App Push notifications
More CA Batch Imports - By Summer?
Push Notifications from Vocalo App - can't miss programming
Accessibility Epic: Text contrast, font size, light/dark options
CA Infrastructre Upgrades.
Archival Search and Retrieval Tool for Journalists' Use
Podcast Player story page template w/ transcript
Related Stories Search improvements
"New from Our Journalists" (like LAist.com)
Homepage Design Refresh
Case Creation with Rest API
Invalidate Unpublished Stories w/out valid Preview URL
Interns Page
NPR One Medium server replacement (tools.wbez.org)
Render Newsletters as Web Pages
FE Map Embed Template
IG Stories Template